Pedro Rodriguez
Honors Thesis Completion Timeline
Axolotl Skin Regeneration and Pigmentation Dynamics

Estimated commitment: 7-10 hours per week.

## Week 1 (Aug 24-30)

Finalize project timeline; review thesis proposal with committee; decide feasibility of image-only analysis versus live axolotl study; organize existing wound-healing image dataset.

## Week 2 (Aug 31-Sep 6)

Conduct literature review on pigmentation regeneration and image-based methodologies; identify image analysis software and measurement protocols.

## Week 3 (Sep 7-13)

Create detailed methodology for both image-only and live-animal pathways; begin pilot measurements on existing wound images.

## Week 4 (Sep 14-20)

Meet with mentor/committee; refine research questions; evaluate quality and quantity of available wound images.

## Week 5 (Sep 21-27)

Develop standardized scoring system for wound closure and pigmentation; continue image collection and organization.

## Week 6 (Sep 28-Oct 4)

Complete methodology draft; determine final study design (image-only or live-animal if approved and feasible).

## Week 7 (Oct 5-11)

Begin formal data collection; measure wound area, closure rate, and pigmentation characteristics from images.

## Week 8 (Oct 12-18)

Continue data collection; verify consistency of measurements; document protocols.

## Week 9 (Oct 19-25)

Complete majority of image analysis; begin preliminary statistical summaries and data visualization.

## Week 10 (Oct 26-Nov 1)

Write Introduction and Literature Review chapters; incorporate recent sources.

## Week 11 (Nov 2-8)

Finish data collection and analysis; generate figures, graphs, and representative image panels.

## Week 12 (Nov 9-15)

Write Methods and Results sections; schedule committee meeting and defense planning.

## Week 13 (Nov 16-22)

Receive feedback from committee; revise thesis draft; strengthen discussion of implications for regenerative biology.

## Week 14 (Nov 23-29)

Write Discussion and Conclusion sections; prepare full thesis draft for review.

## Week 15 (Nov 30-Dec 6)

Submit defense draft to committee; prepare presentation slides and defense materials.

## Week 16 (Dec 7-13)

Conduct thesis defense or mock defense; incorporate final revisions.

## Finals Week (Dec 14-20)

Submit final thesis, PDF, and all required Honors documentation.